## MAP_to_Roles_Steps
| Steps | Details | Assigned | Status
1 | Create sub domains and point to MAP / roles servers. |  | Joseph/Pat | Completed
2 | Update domain and flag fields of the table 'lutPrimaryAgency' in IrrisCentral |  | MAP Team | Completed
3 | Mounting the session folder |  | MAP Team | Completed
4 | Mounting all document folders |  | MAP Team | Manual Process
5 | Create DB copy data from MAP/Roles for each agency(local setup) |  | MAP Team | Completed(local Db)
6 | From MAP DB remove AT users |  | MAP Team | Completed
7 | From MAP Roles keep AT users alone and remove all other users |  | MAP Team | Completed
8 | Run all Script in MAP to add field changes related to roles | Based on Agency | Vince | Pending
9 | Prepare DB scripts for clean up process(need to clean unwanted data once we move the MAP DB to respective agency DB's) |  | MAP Team/Vince | Completed
10 | Prepare DB scripts for insert existing data to newly created tables in IrrisCentral |  | MAP Team | Completed
11 | Make all logical related changes in code |  | MAP Team | Completed
12 | Move all code changes |  | MAP Team | Pending
13 | Create central table for user authentication and agency mapping |  | MAP Team | Completed
14 | Run the DB scripts for insert existing data to newly created tables in IrrisCentral |  | MAP Team | Completed
15 | Create copy MAP DB for each agency(Create copy of MAP for each agency. DB name ends with agency name like (upper case)- MAPHOA, MAPAAI etc.) |  | DB Team/Vince | Completed
16 | Create copy of (taskfreak, QB and Machform) mysql db for each agency ends with agency name(machformAAI, machformHOA etc.) |  | MAP Team | Completed
17 | Run DB scripts for clean up process(need to clean unwanted data once we move the MAP DB to respective agency DB's) | Based on Agency | MAP Team/Vince | Pending
18 | https for subdomain (able access all the sub domain using HTTPS - Listed in Sub Domain Sheet) |  | Pat | Completed
19 | Inform All the Agency to replace the badge code once again from the server. Once we move the subdomain concept to Live ( Machform, External Signup/Signing/Event Badge) | URL Redirections | MAP Team | Completed
20 | Install NSF directory mounting service in all MAP servers |  | Pat | Completed
21 | cfs.myadoptionportal.com pointing to WWW2 |  | Pat | Completed
22 | Manully move CFS related files to Roles |  | MAP Team | Completed
23 | Do smoke testing on entire application in Live |  | All Members

## Sub Domain
agency_id | user_id | agency_name | c_account_key | email_id | Sub Domain Name | address_line_1 | address_line_2 | city | state | zip | country | website | phone | fax | email_id_for_notifications
38 | 437 | Adoption Alliance - Colorado | 15 | info@adoptall.org | aa.myadoptionportal.com | 2121 S. Oneida Street, Suite 420 |  | Denver | Colorado | 80224-2575 | United States of America (USA) | http://www.adoptall.org | 303-584-9900 | 303-584-9007 | Kristeng@adoptall.org
28 | 324 | Adoption Associates Inc. | 109 | adopt@adoptionassociates.net | aai.myadoptionportal.com | 1338 Baldwin St. |  | Jenison | Michigan | 49428-8937 | United States of America (USA) | http://www.adoptionassociates.net | 800-677-2367 | 616-667-0920 | mleahy@adoptionassociates.net
59 | 1554 | Adoption Alliance - Texas | 108 | justin@adoptionalliance.com | aat.myadoptionportal.com | 7303 Blanco Road |  | San Antonio | Texas | 78216 | United States of America (USA) | http://www.adoption-alliance.com/ | 210-349-3991 | 210-349-8975 | NULL
39 | 457 | All Blessings International | 66 | adopt@allblessings.org | abi.myadoptionportal.com | 3808 South Griffith Avenue |  | Owensboro | Kentucky | 42301 | United States of America (USA) | http://www.allblessings.org | 866-543-7459 | 270-684-6748
18 | 166 | A Chosen Child Inc. | 118 | clara@achosenchild.org | acc.myadoptionportal.com | 1516 E. Colonial Drive | Suite 200 | Orlando | Florida | 32803 | United States of America (USA) | http://www.achosenchild.com | 407-894-1599 | 407-895-1599 | linda@strowbridge.com
37 | 384 | Adams Agency | 121 | Adam@adoptsoft.com | adam.myadoptionportal.com | 135 Oakland Road |  | Fairfield | Maine | 4937 | United States of America (USA) |  | 207-314-3984 |  | NULL
27 | 304 | Adoption Dreams Come True | 101 | adoptdreams@yahoo.com | adct.myadoptionportal.com | 316 W. Mulberry |  | Fort Collins | Colorado | 80521 | United States of America (USA) | www.adoptiondreams.org | 970-493-2557 | 970-493-4479 | adoptdreams@yahoo.com
22 | 214 | Adoption and Family Support Center | 120 | elisa568@yahoo.com | afsc.myadoptionportal.com | 709 hills blvd |  | Port Orange | Florida | 32127 | United States of America (USA) | www.adoptfloridafamily | 866-221-6562 | 386-322-3349 | elisa568@yahoo.com
61 | 1876 | ALPTEST | 127 | info@AdoptionLearningPartners.org | alptest.myadoptionportal.com | 2049 Ridge Ave. |  | Evanston | Illinois | 60201 | United States of America (USA) |  | 847-475-5871 |  | NULL
83 | 6774 | Adoptions of Indiana | 141 |  | aoi.myadoptionportal.com | 1980 E. 116th Street, Suite 325 |  | Carmel | Indiana | 46032 | United States of America (USA) | www.adoptionsofindiana.org | 317-574-8950 | 317-574-8971 | NULL
35 | 380 | Adoption Related Services, Inc. | 123 | info@adoption-related-services.org | ars.myadoptionportal.com | 8 South Main Street | P.O. Box 201 | Shrewsbury | Pennsylvania | 17361 | United States of America (USA) | http://www.adoption-related-services.org | 717-227-9560 | 717-227-9562 | barblorenzo@comcast.net
25 | 257 | Adoptions Together | 6 | abache@adoptionstogether.org | at.myadoptionportal.com | 5750 Executive Drive | Suite 107 | Baltimore | Maryland | 21228 | United States of America (USA) | http://www.adoptionstogether.org | 410-869-0620 | 410-402-1122 | mapadmin@adoptionstogether.org
64 | 2372 | Beacon House adoptions | 90 |  | bh.myadoptionportal.com | 5917 Jones Creek Road | Suite 100B | Baton Rouge | Louisiana | 70817 | United States of America (USA) |  | 225-753-5551 | 225-753-6866 | NULL
26 | 266 | CAIRS Solutions | 132 | mark.livings@cairsolutions.com | cairs.myadoptionportal.com | 11643 Grove Street North |  | Seminole | Florida | 33772 | United States of America (USA) |  | 773-750-8284 | 773-750-8284 | mark.livings@cairsolutions.com
79 | 5894 | Connections Adoption Services, Inc. | 87 | mary@connectionsinfo.com | cas.myadoptionportal.com | P.O. Box 182 |  | Raymond | Maine | 4071 | United States of America (USA) | http://www.connectionsadoptionservices.com/ | 800-450-7191 | 207-655-1249 | NULL
81 | 6591 | Catholic Charities of Dallas | 139 | admin@catholiccharitiesdallas.org | ccd.myadoptionportal.com | 9461 LBJ Freeway | Suite 128 | Dallas | Texas | 75243 | United States of America (USA) |  | 214-520-6590 | 214-520-6595 | NULL
74 | 6148 | Catholic Charities of Northern Kansas | 138 | khauser@catholiccharitiessalina.org | cck.myadoptionportal.com | 425 W. Iron Ave. | P. O. Box 1366 | Salina | Kansas | 67402-1366 | United States of America (USA) | www.catholiccharitiessalina.org | 785-825-0208 | 785-826-9708 | NULL
58 | 1423 | Catholic Charities of Southern Nevada | 126 | adoptionservices@catholiccharities.com | ccn.myadoptionportal.com | 1511 Las Vegas Blvd North |  | Las Vegas | Nevada | 89101 | United States of America (USA) | http://www.catholiccharities.com/adoptionservices/adoptioninsouthernnevada.html | 702-385-3351 |  | NULL
17 | 190 | Christian Family Services | 105 | info@cfsfl.org | cfs.myadoptionportal.com | 2720 Southwest Second Ave. |  | Gainesville | Florida | 32607 | United States of America (USA) | www.ChristianFamilyServices.com | 352-378-6202 | 352-378-6205 | moniquel@cfsfl.org
54 | 868 | Cradle | 14 | CAIRSadmin@cradle.org | cradle.myadoptionportal.com | 2049 Ridge Ave. |  | Evanston | Illinois | 60201 | United States of America (USA) |  | 847-475-5800 |  | NULL
1 | 11 | Cradle old | 114 | support@cradle.org | cradle1.myadoptionportal.com | 2049 Ridge Ave. |  | Evanston | Illinois | 60201 | United States of America (USA) |  | 847-475-5800 |  | NULL
43 | 600 | Cradleold2 | 114 | support@cradle.org | cradle2.myadoptionportal.com | 2049 Ridge Ave. |  | Evanston | Illinois | 60201 | United States of America (USA) |  | 847-475-5800 |  | NULL
10 | 98 | Catholic Social Service | 1 | adopt@catholicsocialservice.org | css.myadoptionportal.com | 906 Central Ave |  | Dodge City | Kansas | 67801 | United States of America (USA) | www.catholicsocialservice.org | 620-227-1562 | 620-227-1572 | adopt@catholicsocialservice.org
72 | 4018 | Catholic Social Services, Alaska | 91 | sbomalaski@cssalaska.org | cssa.myadoptionportal.com | 3710 E. 20th Avenue |  | Anchorage | Alaska | 99508 | United States of America (USA) |  | 907-222-7300 | 907-258-1091 | NULL
68 | 2844 | Catholic Social Services of Montana | 99 | helena@cssmt.org | cssmt.myadoptionportal.com | PO Box 907 |  | Helena | Montana | 59624 | United States of America (USA) | www.cssmt.org | 406-442-4130 | 406-442-4192 | admin@cssmt.org
11 | 68 | Cairs Adoption Services | 116 | ryan@adoptsoft.com | delete | 230D RTE 201 |  | Fairfield | Maine | 4937 | United States of America (USA) | www.agency.adoptsoft.com | 207-453-2511
9 | 100 | CAIRS Adoptions | 113 | cairs@adoptsoft.com | delete | 11643 Grove Street |  | Seminole | Florida | 33772 | United States of America (USA) | www.adoptsoft.com | 773-750-8284 |  | cairs@adoptsoft.com
65 | 0 | MAPRole Test Agency | 130 |  | delete | 81 Pleasant St. |  | clinton | Maine | 4927 | United States of America (USA) |  | 207-666-9999 |  | NULL
78 | 5624 | Media Systems | 79 | hradmin@admin.com | demo.myadoptionportal.com | Leela Infopark | Phase ¦¦ | Kochi | Arizona | 678543 | United States of America (USA) | www.msi.com | 976-665-5555 | 456-765-7657 | hradmin@admin.com
31 | 341 | Deaconess Pregnancy and Adoption Services | 104 |  | dpas.myadoptionportal.com | 7101 NW Expressway, | Suite 325 | Oklahoma City | Oklahoma | 73132 | United States of America (USA) | http://www.deaconessadoption.org/ | 405-949-4200 |  | NULL
82 | 6753 | Embraced by Grace | 140 | adoption@embracedbygrace.org | ebg.myadoptionportal.com | 447 South Nova Rd. |  | Ormond Beach | Florida | 32174 | United States of America (USA) | http://www.embracedbygrace.org | 386-615-9767 | 386-615-9792 | adoption@embracedbygrace.org
40 | 458 | European Children Adoption Services | 67 |  | ecas.myadoptionportal.com | 6050 Cheshire Lane North |  | Plymouth | Minnesota | 55446 | United States of America (USA) | http://www.ecasus.org/ | 763-694-6131 | 763-694-6104 | NULL
71 | 3035 | Eckerd Community Alternatives | 133 |  | eckerd.myadoptionportal.com | Camelot Community Care | 4910 Creekside Dr, Ste D | Clearwater | Florida | 33760 | United States of America (USA) |  | 727-593-0003 |  | NULL
77 | 5017 | Family Adoption Consultants | 17 | kathyluz@facadopt.org | fac.myadoptionportal.com | 45100 Sterritt Street, Suite 203 |  | Utica | Michigan | 48317 | United States of America (USA) | http://facadopt.org | 586-726-2988 | 586-726-2599 | NULL
34 | 366 | A Gift of Life | 122 | info@giftoflifeadoptions.com | gol.myadoptionportal.com | 4437 Park Boulevard |  | Pinellas Park | Florida | 33781-3540 | United States of America (USA) | http://www.giftoflifeadoptions.com/ | 727-549-1416 | 727-548-8174 | admin@giftoflifeadoptions.com
42 | 597 | Hawaii International Child | 52 | KCastagnaro@h-i-c.org | hic.myadoptionportal.com | 1168 Waimanu Street |  | Honolulu | Hawaii | 96814 | United States of America (USA) | http://www.h-i-c.org/index.php | 808-589-2367 | 808-593-2247 | adopt@h-i-c.org
21 | 194 | Heart of Adoptions, Inc. | 95 | jessica@heartofadoptions.com | hoa.myadoptionportal.com | 418 West Platt Street | Suite A | Tampa | Florida | 33606 | United States of America (USA) | http://www.heartofadoptions.com | 800-590-1108 | 813-254-9058 | Jessica@heartofadoptions.com
76 | 4816 | International Families, Inc. | 88 |  | ifi.myadoptionportal.com | 5 Thomas Circle, NW |  | Washington DC | District of Columbia | 20005 | United States of America (USA) |  | 202-667-5779 |  | NULL
44 | 695 | Living Hope Adoption Agency | 45 | info@livinghopeadoption.org | lh.myadoptionportal.com | 449 Pennsylvania Ave |  | Fort Washington | Pennsylvania | 19034 | United States of America (USA) | livinghopeadoption.org | 888-886-8086 |  | info@livinghopeadoption.org
30 | 338 | Little Miracles International Inc. | 51 | info@littlemiracles.org | lmi.myadoptionportal.com | 600 S Tyler St | Suite 1302 | Amarillo | Texas | 79101 | United States of America (USA) | www.littlemiracles.org | 806-351-1100 |  | deborah@littlemiracles.org
66 | 2559 | Lutheran Social Services Of Montana | 131 |  | lssmt.myadoptionportal.com | 2429 Mission Way |  | Billings | Montana | 59102 | United States of America (USA) | http://www.lssmt.org/ | 406-245-9949 | 406-655-7729 | lssmtadmin@lssmt.org
4 | 34 | MTA2 | 113 |  | mta2.myadoptionportal.com | 11643 Grove Street |  | Seminole | Florida | 33772 | United States of America (USA) |  | 773-750-8284 |  | NULL
24 | 613 | One World Adoption Services | 124 | main@oneworldadoptions.org | owas.myadoptionportal.com | 1400 Buford Highway Suite L-4 |  | Sugar Hill | Georgia | 30518 | United States of America (USA) | www.oneworldadoptions.org | 770-965-3744 | 770-965-6632 | main@oneworldadoptions.org
69 | 2864 | Premier Adoption | 28 | isa@premieradoption.org | paa.myadoptionportal.com | 590 W. Mesquite Blvd., Ste. 202B |  | Mesquite | Nevada | 89027 | United States of America (USA) |  | 702-346-4922 |  | admin@premieradoption.org
57 | 1419 | Surrogacy Choices LLC | 125 |  | scl.myadoptionportal.com | 789 E. 2nd Street |  | Reno | Nevada | 89502 | United States of America (USA) | www.e-surrogacy.com | 888-336-4068 |  | surrattlaw@gmail.com
16 | 185 | St. Mary's Services | 117 | information@stmaryservices.com | sms.myadoptionportal.com | 717 W. Kirchhoff Road | Arlington Heights, | Chicago | Illinois | 60005 | United States of America (USA) | http://www.stmaryservices.com | 888-786-2797 | 847-870-8325
32 | 347 | Sunny Ridge Family Center | 33 | kgraham@sunnyridge.org | sr.myadoptionportal.com | 270 Remington Boulevard, Suite C |  | Bolingbrook | Illinois | 60440 | United States of America (USA) | http://www.sunnyridge.org | 630-754-4500 |  | NULL
19 | 174 | TDH | 34 | dorinda@tdh.ca | tdh.myadoptionportal.com | 2520 Lionel Groulx | Third floor | Montreal | Other | H93J1J8 | Canada | www.tdh.ca | 514-937-3325 | 514-933-7125 | dorinda@tdh.ca
20 | 355 | Zdoptions | 119 | info@zdoptions.com | zdopt.myadoptionportal.com | 123 MainSt |  | Miami | Florida | 33361 | United States of America (USA) | Zdoptions.com | 555-555-5555 |  | NULL

## allocation and Estimation
| Task | Description | Comments | Estimated Hours |  |  | Status | Assigned | Status-Testing | Remarks
| Initial Documentations & Analysis | [5 empty] | Completed | Dennis
1 | Create new table 'map_user_accounts' in IrrisCentral | Fields are 'map_user_id'(primary key), 'map_username', 'map_password','map_encryption' | For each user there must be a row in 'map_user_table' with unique 'map_username' and 'map_user_id' fields. 'map_encryption' field used to identify the password encryption type(sha1 or 64bit encryption) | 1 | 2012-12-07 | 2012-12-07 | Completed | Hari | Passed
2 | Insert existing data from MAP and Roles to new table 'map_user_accounts' | Fetch the username, password and encryption type from user_accounts table and insert it to the new table 'map_user_accounts' |  | 2 | 2012-12-07 | 2012-12-07 | Completed | Hari | Passed
3 | Create new table 'map_user_agencies' | Fields are 'id'(primary key), 'map_user_id', 'map_agency_id', 'user_id' | map_user_id' pointing to the primary key in 'map_user_accounts' table. 'map_agency_id' is the 'c_account_key' in the 'user_agencies' table and 'user_id' is pointing to the primary key in 'user_accounts' table | 1 | 2012-12-07 | 2012-12-07 | Completed | Hari | Passed
4 | Insert existing data from MAP and Roles to new table 'map_user_agencies' | Fetch the user_id from user_accounts table and corresponding 'map_user_id' from 'map_user-accounts' table. Also fetch the 'c_account_key' from user_agencies table. Then insert these values to map_user_agencies table |  | 3 | 16/7/2012 | 16/7/2012 | Completed | Hari/Dennis | Passed
5 | Add three fields 'subDomain', 'agDbName' and 'existInMap' | 'subDomain' has the Domain name of that agency, 'agDbName' has the Agency DB name and 'existInMap' is a flag to identify tghat agency is exist in MAP or not |  | 1 | 2012-12-07 | 2012-12-07 | Completed | Hari | Passed
6 | create one file authenticate_map_phpfunctions.php in admin folder | This file is for writing all the common functions for authentication |  | 0.5 | 2012-12-07 | 2012-12-07 | Completed | Hari | Passed
7 | create a new function 'authenticate-map_use' for authenticate users | Pass the username and password as the parameters. Authenticate username and password in map_user_accounts table |  | 2 | 13/7/2012 | 13/7/2012 | Completed | Prashanth/ Hari | Passed
8 | Create new function authenticate_map_user_agency for getting agency information | pass map_user_id as the parameter and using this fetch map_agency_id from map-user-agencies table. Using map_agency_id fetch all agency data from user_agencies |  | 3 | 13/7/2012 | 2012-12-03 | Completed | Prashanth/ Hari | Passed
9 | Based on the sub domain, redirecting to session.php with session ID as parameter | Inorder to get the sesion values to all sub domains we are passing the session ID as a parameter and using this session ID we can fetch all session variables in all subdomains |  | 3 | 13/7/2012 | 13/7/2012 | Completed | Prashanth/ Hari | Passed
10 | write a function 'authenticate_map_dbname' to get the DB name based on the domain name | Passing domain name as parameter and get the database name from 'lutPrimaryAgency' table in IrrisCentral |  | 3 | 16/7/2012 | 16/7/2012 | Completed | Prashanth/ Hari | Passed
11 | In command.php file set the database name variable based on agency selection | Using 'authenticate_map_dbname' function get the corresponding DB name and assign that to DB name variable |  | 1 | 16/7/2012 | 16/7/2012 | Completed | Hari | Passed
12 | create a function 'authenticate_update_central' to insert and update the newly added central tables | passin user_id and map_user_id as parameters and get username, password and encryption method from user_accounts and insert in to the new table 'map_user_accounts'. Also fetch the 'c_account_key' from user_agencies table. Then insert these values to map_user_agencies table |  | 3 | 16/7/2012 | 16/7/2012 | Completed | Hari | Passed
13 | Create an interface for selecting agency when a user login | When a user trying to login, before going to the home page we are provide an inerface to select an agency |  | 18 | 17-7-2012 | 19-7-2012 | Completed | Dennis | Passed
14 | Once user select an agency, we are setting the session values | Get all the required data from the function authenticate_map_user_agency and assign it to each session variables. |  | 2 | 17-7-2012 | 17-7-2012 | Completed | Prashanth/ Hari | Passed
19 | Change the signup functionality | when click on signup we are going to add interface for selecting the agency. |  | 5 | 20-7-2012 | 20-7-2012 | Completed | Hari | Passed
20 |  | after selecting the agency we are directing to signup page and in that page we are going to remobve the agency selection |  | 4 | 20-7-2012 | 23-7-2012 | Completed | Prashanth/ Hari | Passed
26 | User updation as portal admin | Need to update the password in IrrisCentral |  | 2 | 23-7-2012 | 23-7-2012 | Completed | Prashanth | Passed
27 | Change password in account info | Need to update the password in IrrisCentral |  | 1 | 23-7-2012 | 23-7-2012 | Completed | Prashanth | Passed
28 | User deletion need to be handled in Common tables of IrrisCentral | need to update the status flag in 'map_user_agencies' in IrrisCentral |  | 2 | 23-7-2012 | 23-7-2012 | Completed | Prashanth | passed
35 | Virtual Host Setup /R&D Testing - Local environment setup |  | Extra Works | 8 | 18-7-2012 | 18-7-2012 | Completed | Hari | Passed
36 | Compare schema objects of both [MapRole] and [MyAdoptionPortalV2] |  | Extra Works | 0.5 | 16-07-2012 | 16-07-2012 | Completed | Jithin | Jithins part
37 | Compare schema objects of both [Demo] and [MyAdoptionportalTestNew] |  | Extra Works | 0.5 | 16-07-2012 | 16-07-2012 | Completed | Jithin | Jithins part
38 | Prepare and Execute migration script for [MapRoleMigration] which contains schema objects of both [MapRole] and [MyAdoptionPortalV2]. |  |  | 6 | 16-07-2012 | 17-07-2012 | Completed | Jithin | Jithins part
39 | Prepare and Execute migration script for [DemoMigration] which contains the schema objects of both [Demo] and [MyAdoptionportalTestNew]. |  |  | 1 | 17-07-2012 | 17-07-2012 | Completed | Jithin | Jithins part
30 | need to take the password from 'map_user_accounts' | Currently we are fetching password from user accounts table and we need to fetch it from 'map_user_accounts' once we use separate DB agencies |  | 1 | 24-7-2012 | 24-7-2012 | Completed | Prashanth | Passed
32 | add one more column 'status' in 'map_user_agencies' and while login need to check this column also. | Need to check new status column is active in 'map_user_agencies' while login |  | 1 | 24-7-2012 | 24-7-2012 | Completed | Prashanth | passed
34 | Find and list down all the SUB domains | Sub domains are different for different agencies and we need to find out and list down all the SUB domains |  | 2 | 25-7-2012 | 25-7-2012 | Completed | Prashanth | Passed
29 | User deleteion for users under multiple agencies | if it’s a permenant delete by portal admin and user is under multiple agencies, we need to check the active user mapping in 'map_user_agencies' and if there is no such row is there we need to remove that user from 'map_user_accounts' in IrrisCentral |  | 3 | 24-7-2012 | 24-7-2012 | Completed | Prashanth | passed
16 | Need to change the password updation table to 'map_user_accounts' in IrrisCentral | Currently we update the password in user_accounts table only But as per the new logic we need to update this in 'map_user_accounts' in IrrisCentral |  | 2 | 18-7-2012 | 18-7-2012 | completed | Prashanth | Passed
17 | Forgot password should be based on username | currently forgot password functionality worked based on email field. Need to changes this to username field |  | 1 | 18-7-2012 | 18-7-2012 | completed | Hari | Passed
18 | Forgot password functionality in signup link | Need to change the forgot password functionality in signup link |  | 8 | 19-7-2012 | 19-7-2012 | completed | Hari | Passed
21 | Change the signup functionality in Signup badge | Need to do the same signup functionality changes in Signup badge |  | 8 | 19-7-2012 | 20-7-2012 | completed | Hari | Passed
22 | Change the signup functionality in Event badge | Need to do the same signup functionality changes in Event badge |  | 6 | 20-7-2012 | 20-7-2012 | completed | Prashanth | Passed
23 | Change the signup functionality in Event registration | Need to do the same signup functionality changes in Event registration |  | 8 | 20-7-2012 | 23-7-2012 | completed | Prashanth | Passed
24 | Change the signup functionality in Inquiry badge | Need to do the same signup functionality changes in Inquiry badge |  | 6 | 23-7-2012 | 23-7-2012 | completed | Prashanth | Passed
25 | While updating a user make the updations in 'map_user_accounts' in IrrisCentral | While updating a user make the updations in 'map_user_accounts' in IrrisCentral |  | 3 | 23-7-2012 | 23-7-2012 | completed | Prashanth | passed
15 | Change the logic of Forgot password | When user enter the email address, send confirmation mail with encrypted userid and when user click the enable link in the email, we will generate the new password and send one mail with this new password. | In current forgot password logic, we changed the password immediately when anyone enter the emailid. | 6 | 17-7-2012 | 18-7-2012 | Inprogress | Prashanth/ Hari | Passed
31 | Need to change the all cronjob logic to handle multiple DB | Need to change the all cronjob logic to handle multiple DB |  | 10 | 2012-07-24 | 26-7-2012 | Scheduled | Dennis | Passed
33 | Once we move the MAP and Roles tables to agency DB, we need to clean up all the data's of all other agencies | Once we move the MAP and Roles tables to agency DB, we need to clean up all the data's of all other agencies |  | 15 | 24-7-2012 | 25-7-2012 | Scheduled | Dennis | Scheduled
40 | Change the configureation page to connect MAP support system based on sub-domain (Taskfreak, QB, Machform) |  |  | 20 | 2012-07-23 | 2012-07-23 | Scheduled | Dennis | Passed

## Challenges
| Issues | Comments
1 | Login as Portal Admin | As per the new plan we have different DB for different Agencies. So if login as portal admin we have lot of Challenges
2 | Agency Creation Interface
3 | All kind of duplication
4 | User creation in mac form
5 | Task freak, Machform and QB are the integrated systems with MAP and most of the logic is based on the unique user_id.
a. Each agency will have copy of MAP and will repeat the userid across agencies and cannot be handled with common MySQL DB
b. Solution : Need to have copy of MySQL db for each agency ( DB Name ends with agency domain name – machformAAI, taskfreakAAI, quickbookAAI etc.)
6 | Keeping the Username/Password uniqueness across agencies.
a. Here user can sign up to different agency with same email and different password.
b. How can we handle the username uniqueness between agencies if they use this scenario.
c. Solution: We can consider them as separate user if the password is not the same.
d. Solution: If the username/password is same, we can attach the same user internally to new agency in agency user mapping.
e. Solution: We provide them interface to choose agency if they sign up to multiple agencies.
7 | Cron job
a. Currently cron job is running for one common domain with one DB
b. Here each agency will be identified by sub-domain and each one will have each MAP DB.
c. Solution : Cron job needs to be executed for each agency and it should internally connect to the respective agency DB.
d. Solution: Triggering of external email from cron job should point to the corresponding sub-domain of the agency.
Pending Development Tasks (Estimated Hours – 70 Hrs of development) and then need to test the whole system in the new server.

## DB scripts
population of data map_user_agencies table
truncate table [IrrisCentral].[dbo].[map_user_agencies];
GO
truncate table [IrrisCentral].[dbo].[map_user_accounts];
GO
INSERT INTO [IrrisCentral].[dbo].[map_user_accounts] (map_username,map_password,map_encryption)
(SELECT username,password,new_encryption FROM MyAdoptionPortalV2.[dbo].user_accounts);
Go
INSERT INTO [IrrisCentral].[dbo].[map_user_agencies] (map_user_id,map_agency_id,user_id,status)
(SELECT ir.map_user_id,u.c_account_key,ua.user_id,ua.status FROM MyAdoptionPortalV2.[dbo].user_accounts ua JOIN
MyAdoptionPortalV2.[dbo].user_agencies u ON ua.agency_id= u.agency_id JOIN
[IrrisCentral].[dbo].[map_user_accounts] ir ON ir.map_username=ua.username);
GO
INSERT INTO [IrrisCentral].[dbo].[map_user_accounts] (map_username,map_password,map_encryption)
(SELECT username,password,new_encryption FROM MyAdoptionPortal.[dbo].user_accounts)
GO
INSERT INTO [IrrisCentral].[dbo].[map_user_agencies] (map_user_id,map_agency_id,user_id,status)
(SELECT ir.map_user_id,u.c_account_key,ua.user_id,ua.status FROM MyAdoptionPortal.[dbo].user_accounts ua JOIN
MyAdoptionPortal.[dbo].user_agencies u ON ua.agency_id= u.agency_id JOIN
[IrrisCentral].[dbo].[map_user_accounts] ir ON ir.map_username=ua.username);
GO
update [IrrisCentral].[dbo].[map_user_accounts] set map_encryption='N' where map_encryption is null
GO
select count(*) from [IrrisCentral].[dbo].[map_user_accounts];
GO
select count(*) from [IrrisCentral].[dbo].[map_user_agencies];
GO
select distinct map_encryption from [IrrisCentral].[dbo].[map_user_accounts];
MAP URL Redirections
/* for MAP */
inser Query for redirecting badges
For signing in badge
---------------------
INSERT INTO [IrrisCentral].[dbo].[redirctUrl]
([fromUrl]
,[toUrl])
Select | 'http://www.myadoptionportal.com/myportal.php?key_id=' + Cast(agency_id As Varchar(5)),
http://'+lut.subDomain+'/myportal.php?key_id=' + Cast(agency_id As Varchar(5))
from | MyAdoptionPortal.dbo.user_agencies ua
JOIN | [IrrisCentral].[dbo].lutPrimaryAgency lut on ua.c_account_key = lut.SiteID and lut.agencyFlag in('R','M')
Note:- For 'At' we need to change fromurl as 'www2' instead of 'www'
For signup badge
----------------
INSERT INTO [IrrisCentral].[dbo].[redirctUrl]
([fromUrl]
,[toUrl])
Select | 'http://devroles.myadoptionportal.com/signupmp.php?pluginoption=userslogin&type=signup&key_id=' + Cast(agency_id As Varchar(5)),
http://'+lut.subDomain+'/signupmp.php?pluginoption=userslogin&type=signup&key_id=' + Cast(agency_id As Varchar(5))
from | MyAdoptionPortal.dbo.user_agencies ua
JOIN | [IrrisCentral].[dbo].lutPrimaryAgency lut on ua.c_account_key = lut.SiteID and lut.agencyFlag in('R','M')
Note:- For 'At' we need to change fromurl as 'www2' instead of 'www'
For event badge
---------------
INSERT INTO [IrrisCentral].[dbo].[redirctUrl]
([fromUrl]
,[toUrl])
Select | 'http://devroles.myadoptionportal.com/signupmp.php?pluginoption=userslogin&type=signup&key_id=' + Cast(key_content As Varchar(MAX)),
http://'+lut.subDomain+'/signupmp.php?pluginoption=userslogin&type=signup&key_id=' + Cast(key_content As Varchar(MAX))
from | MyAdoptionPortal.dbo.eventscalendar_viewkeys ec
JOIN MyAdoptionPortal.dbo.user_agencies ua on ua.agency_id = ec.agency_id
JOIN | [IrrisCentral].[dbo].lutPrimaryAgency lut on ua.c_account_key = lut.SiteID and lut.agencyFlag in('R','M')
Note:- For 'At' we need to change fromurl as 'www2' instead of 'www'
for mach form - need to inser manually

## mounting folder list
Description | Folder
Casenote upload | /var/www/html/casefile
Machform form files | /var/www/html/eform/data
creating signatures of the users | /var/www/html/payement/onlinesignature
Payment related doc | /var/www/html/payment/document
payment pdf creator | /var/www/html/payment/pdf
Report XML Files | /var/www/html/report/app/xml
User Images | /var/www/html/upload/user_images | scp -r /var/www/html/upload/user_images/* root@192.168.1.21:/var/www/html/upload/user_images
| /var/www/html/upload/user_pdfs | scp -r /var/www/html/upload/user_pdfs/* root@192.168.1.21:/var/www/html/upload/user_pdfs
agency images(static) | /var/www/html/userhome/agency
billing invoice pdf | /var/www/html/userhome/billing | scp -r /var/www/html/userhome/billing/* root@192.168.1.21:/var/www/html/userhome/billing
Casenote repository | /var/www/html/userhome/casenotes
events | /var/www/html/userhome/eventscalendar | scp -r /var/www/html/userhome/eventscalendar/* root@192.168.1.21:/var/www/html/userhome/eventscalendar
Forms related files | /var/www/html/userhome/formmaker | scp -r /var/www/html/userhome/formmaker/* root@192.168.1.21:/var/www/html/userhome/formmaker
messages | /var/www/html/userhome/messages
| /var/www/html/userhome/pdf | scp -r /var/www/html/userhome/pdf/* root@192.168.1.21:/var/www/html/userhome/pdf
uploading form template pdf | /var/www/html/userhome/printcontent
storing session | /var/www/html/userhome/sessions
PDF Templates | /var/www/html/userhome/template
Tiny MCE Files | /var/www/html/userhome/userfiles
User files | /var/www/html/userhome/users
Folder Conversion based on Agency
Online Signature | https://www.myadoptionportal.com/createAgencyFolder.php
Machform | https://www.myadoptionportal.com/createAgencyFolderEform.php
TinyMCE Folder | https://www.myadoptionportal.com/createAgencyFolder_1.php
Online Signature | https://www2.myadoptionportal.com/createAgencyFolder.php
Machform | https://www2.myadoptionportal.com/createAgencyFolderEform.php
TinyMCE Folder | https://www2.myadoptionportal.com/createAgencyFolder_1.php
Files Transfer to Roles Server
Run the php file in command prompt and modify the agency ID inside the file | createAgencyFiles.php
Backup all PHP Files(linux command)
rsync -avm --include='*.php' -f 'hide,! */' . /var/www/htmlbackup12-08-12/

## settings changes
1 | Please add following lines to $eetings.php file. This is for mysql connection. $db["mysqlhostname"]="localhost"; $db["mysqlusername"]="root"; $db["mysqlpassword"]="media"; $db["qbmysqlcon"]= "mysql://root:media@localhost/quickbooks_api".$_SESSION['SiteAbbrev']; $db["mysqlqbdbname"]="quickbooks_api".$_SESSION['SiteAbbrev']; $db["mysqltaskfrkdbname"]="taskfreak".$_SESSION['SiteAbbrev']; $db["mysqlmacformdbname"]="mapmachform".$_SESSION['SiteAbbrev']; and please make the below change in eform/ config.php in line 8, define('DB_NAME', $db["mysqlmacformdbname"]); define('DATA_DIR', './data/'.$_SESSION['SiteAbbrev']); define('UPLOAD_DIR', './data'.$_SESSION['SiteAbbrev']); and please make the below change in task/include/ config.php in line 16, define('TZN_DB_BASE',$db["mysqltaskfrkdbname"]);
2 | Following cron job files have different conditions in MAP and ROLES, taskalert.php reference_mailtrigger.php taskscheduler.php get_agencyID.php taskFreakUserSync.php

## Checklist
File Name
Files moved to both MAP and Roles
/www.myadoptionportal.com.PV.5.0/admin/authenticate_phpfunctions.php
/www.myadoptionportal.com.PV.5.0/admin/command.php
/www.myadoptionportal.com.PV.5.0/admin/signature_functions.php
/www.myadoptionportal.com.PV.5.0/agency/financesettings.php
/www.myadoptionportal.com.PV.5.0/agency_portal.php
/www.myadoptionportal.com.PV.5.0/agencyselection.php
/www.myadoptionportal.com.PV.5.0/airs/cw_client_list.php
/www.myadoptionportal.com.PV.5.0/authenticate_session.php
/www.myadoptionportal.com.PV.5.0/auxiliary/editor/filemanager/connectors/php/config.php
/www.myadoptionportal.com.PV.5.0/auxiliary/js/map_flexpaper.js
/www.myadoptionportal.com.PV.5.0/auxiliary/signature/code/single_signature/map_user_signature_save.php
/www.myadoptionportal.com.PV.5.0/auxiliary/signature/map_signature_process.php
/www.myadoptionportal.com.PV.5.0/auxiliary/signature/map_signature_process_payment.php
/www.myadoptionportal.com.PV.5.0/auxiliary/signature/map_signature_process_updation_validation.php
/www.myadoptionportal.com.PV.5.0/auxiliary/signature/map_signature_process_updation_validation_payment.php
/www.myadoptionportal.com.PV.5.0/eform/save.php
/www.myadoptionportal.com.PV.5.0/eform/view.php
/www.myadoptionportal.com.PV.5.0/eventscalendar.php
/www.myadoptionportal.com.PV.5.0/eventscalendar/phpfunctions.php
/www.myadoptionportal.com.PV.5.0/formmaker/menu-activity.php
/www.myadoptionportal.com.PV.5.0/formmaker/menu-managesubmissions2.php
/www.myadoptionportal.com.PV.5.0/get_agencyID.php
/www.myadoptionportal.com.PV.5.0/get_agencyID_action.php
/www.myadoptionportal.com.PV.5.0/header.php
/www.myadoptionportal.com.PV.5.0/myportal.php
/www.myadoptionportal.com.PV.5.0/payment/ap_viewInvoiceprint.php
/www.myadoptionportal.com.PV.5.0/payment/pdfCreate 2.php
/www.myadoptionportal.com.PV.5.0/payment/pdfCreate.php
/www.myadoptionportal.com.PV.5.0/payment/pdfCreate1.php
/www.myadoptionportal.com.PV.5.0/payment/pdfCreate4.php
/www.myadoptionportal.com.PV.5.0/payment/signature_check.php
/www.myadoptionportal.com.PV.5.0/plugin-accountlogin.php
/www.myadoptionportal.com.PV.5.0/quickbook/qb_header.php
/www.myadoptionportal.com.PV.5.0/quickbook/qboe_import_export.php
/www.myadoptionportal.com.PV.5.0/reference_mailtrigger.php
/www.myadoptionportal.com.PV.5.0/reference_mailtrigger_action.php
/www.myadoptionportal.com.PV.5.0/relay_authorize_form.php
/www.myadoptionportal.com.PV.5.0/relay_authorize_paypal1.php
/www.myadoptionportal.com.PV.5.0/report/app/dbconnect.php
/www.myadoptionportal.com.PV.5.0/signupmp.php
/www.myadoptionportal.com.PV.5.0/surveypro/emailref_plugin-body.php
/www.myadoptionportal.com.PV.5.0/surveypro/menu-campaignview.php
/www.myadoptionportal.com.PV.5.0/surveypro/menu-manageQA.php
/www.myadoptionportal.com.PV.5.0/surveypro/reference_client.php
/www.myadoptionportal.com.PV.5.0/surveypro/reference_menu.php
/www.myadoptionportal.com.PV.5.0/surveypro/reference_signcheck.php
/www.myadoptionportal.com.PV.5.0/surveypro/referenceresult.php
/www.myadoptionportal.com.PV.5.0/surveypro/referenceresult_client.php
/www.myadoptionportal.com.PV.5.0/surveypro/xml/referencestatus_formxml.php
/www.myadoptionportal.com.PV.5.0/surveypro/xml/referencestatus_formxml_client.php
/www.myadoptionportal.com.PV.5.0/taskalert.php
/www.myadoptionportal.com.PV.5.0/taskalert_action.php
/www.myadoptionportal.com.PV.5.0/taskFreakUserSync.php
/www.myadoptionportal.com.PV.5.0/taskFreakUserSync_action.php
/www.myadoptionportal.com.PV.5.0/taskscheduler.php
/www.myadoptionportal.com.PV.5.0/taskscheduler_action.php
/www.myadoptionportal.com.PV.5.0/users/accountlogin.php
/www.myadoptionportal.com.PV.5.0/users/accountlogin1.php
/www.myadoptionportal.com.PV.5.0/users/change_password.php
/www.myadoptionportal.com.PV.5.0/users/confirmation.php
/www.myadoptionportal.com.PV.5.0/users/filePreview.php
/www.myadoptionportal.com.PV.5.0/users/menu-accounts.php
/www.myadoptionportal.com.PV.5.0/users/phpfunctions.php
/www.myadoptionportal.com.PV.5.0/users/selectBaseAgency.php
/www.myadoptionportal.com.PV.5.0/users/userloginhelp.php
/www.myadoptionportal.com.PV.5.0/webservice/inquiry/inquiry_webservice_functions.php
/www.myadoptionportal.com.PV.5.0/xmls/formmaker/documentListing.php
Folders
admin
agency
airs
auxiliary
eform
eventscalendar
formmaker
payment
quickbook
report
surveypro
users
webservice
xmls

## DB Cleanup
select * from user_agencies where agency_id not in (
select agency_id from test_agency
)
select * from test_agency
--insert into test_agency values (25)
#NAME?
--insert into test_agency select agency_id from user_agencies where user_id not in (266,257)
select * from user_accounts where user_id=266
select * from user_accounts where user_id=257
Select 'Drop Table formmaker_'+formname from formmaker_properties where form_agency_id in (select agency_id from test_agency)
union
Select 'Drop Table formmaker_'+formname+'_tmp' from formmaker_properties where form_agency_id in (select agency_id from test_agency);
GO
delete from formmaker_submissions where form_id in
(select form_id from formmaker_properties where form_agency_id in (select agency_id from test_agency));
GO
delete from formmaker_fields where page_id in
(select page_id from formmaker_pages where form_id in
(select form_id from formmaker_properties where form_agency_id in (select agency_id from test_agency)));
GO
delete from formmaker_pages where form_id in
(select form_id from formmaker_properties where form_agency_id in (select agency_id from test_agency));
GO
delete from formmaker_properties where form_agency_id in (select agency_id from test_agency);
GO
delete from formmaker_fieldoptions where field_id not in ( select field_id from formmaker_fields)
GO
delete from user_accounts where agency_id in (select agency_id from test_agency);
GO
delete from formmaker_phases where agency_id in (select agency_id from test_agency);
GO
delete from formmaker_stages where phase_id not in (select phase_id from formmaker_phases);
GO
delete from formmaker_tasks where phase_id not in (select phase_id from formmaker_phases);
GO
delete from formmaker_taskstatus where phase_id not in (select phase_id from formmaker_phases);
GO
truncate table error_log
GO
truncate table ErrorLog
GO
truncate table user_logs
GO
truncate table MAPAIRSSynchronization
GO
delete from user_agencies where agency_id in(select agency_id from test_agency);
GO
truncate table audit_trial
GO
sp_helpdb MyAdoptionPortalV2
use MyAdoptionPortalV2;
GO
--DBCC SHRINKFILE (MyAdoptionPortal);
--DBCC SHRINKFILE (MyAdoptionPortal_log);

## Agency Details
C_Account_Key | AgencyName | MAP_Agency_DB_Name | Agency_Sub_Domain_Name | Flag_MAP_ or_in_Roles | AIRS_DB_Name | TaskFreak | QuickBook | MachForm
118 | A Chosen Child Inc. | MAPACC | acc.myadoptionportal.com | M | acc | taskfreakACC | quickbook_apiACC | mapmachformACC
122 | A Gift of Life | MAPGOL | gol.myadoptionportal.com | M | gol | taskfreakGOL | quickbook_apiGOL | mapmachformGOL
121 | Adams Agency | MAPADAM | adam.myadoptionportal.com | M | Adam | taskfreakADAM | quickbook_apiADAM | mapmachformADAM
15 | Adoption Alliance - Colorado | MAPAA | aa.myadoptionportal.com | M | aa | taskfreakAA | quickbook_apiAA | mapmachformAA
108 | Adoption Alliance - Texas | MAPAAT | aat.myadoptionportal.com | M | AAT | taskfreakAAT | quickbook_apiAAT | mapmachformAAT
120 | Adoption and Family Support Center | MAPAFSC | afsc.myadoptionportal.com | M | AFSC | taskfreakAFSC | quickbook_apiAFSC | mapmachformAFSC
109 | Adoption Associates Inc. | MAPAAI | aai.myadoptionportal.com | M | AAI | taskfreakAAI | quickbook_apiAAI | mapmachformAAI
101 | Adoption Dreams Come True | MAPADCT | adct.myadoptionportal.com | M | adct | taskfreakADCT | quickbook_apiADCT | mapmachformADCT
123 | Adoption Related Services, Inc. | MAPARS | ars.myadoptionportal.com | M | ARS | taskfreakARS | quickbook_apiARS | mapmachformARS
141 | Adoptions of Indiana | MAPAOI | aoi.myadoptionportal.com | M | AoI | taskfreakAOI | quickbook_apiAOI | mapmachformAOI
136 | Adoptions Together | MAPAT | at.myadoptionportal.com | R | ATMap | taskfreakAT | quickbook_apiAT | mapmachformAT
66 | All Blessings International | MAPABI | abi.myadoptionportal.com | M | ka | taskfreakABI | quickbook_apiABI | mapmachformABI
127 | ALPTest | MAPALPTEST | alptest.myadoptionportal.com | M | ALPTest | taskfreakALPTEST | quickbook_apiALPTEST | mapmachformALPTEST
90 | Beacon House adoptions | MAPBH | bh.myadoptionportal.com | M | BH | taskfreakBH | quickbook_apiBH | mapmachformBH
132 | CAIRS Solutions | MAPCAIRS | cairs.myadoptionportal.com | M | CSI | taskfreakCAIRS | quickbook_apiCAIRS | mapmachformCAIRS
139 | Catholic Charities of Dallas | MAPCCD | ccd.myadoptionportal.com | M | CCD | taskfreakCCD | quickbook_apiCCD | mapmachformCCD
138 | Catholic Charities of Northern Kansas | MAPCCK | cck.myadoptionportal.com | M | CCK | taskfreakCCK | quickbook_apiCCK | mapmachformCCK
126 | Catholic Charities of Southern Nevada | MAPCCN | ccn.myadoptionportal.com | M | CCN | taskfreakCCN | quickbook_apiCCN | mapmachformCCN
1 | Catholic Social Services | MAPCSS | css.myadoptionportal.com | M | css | taskfreakCSS | quickbook_apiCSS | mapmachformCSS
99 | Catholic Social Services of Montana | MAPCSSMT | cssmt.myadoptionportal.com | M | CSSMT | taskfreakCSSMT | quickbook_apiCSSMT | mapmachformCSSMT
91 | Catholic Social Services, Alaska | MAPCSSA | cssa.myadoptionportal.com | M | CSSA | taskfreakCSSA | quickbook_apiCSSA | mapmachformCSSA
163 | cdmap01.myadoptionportal.com | MyAdoptionPortalT2 | cdmap01.myadoptionportal.com | R | MapRole | taskfreakCDMAP01 | quickbook_apiCDMAP01 | mapmachformCDMAP01
105 | Christian Family Services | MAPCFS | cfs.myadoptionportal.com | M | CFS | taskfreakCFS | quickbook_apiCFS | mapmachformCFS
87 | Connections Adoption Services, Inc. | MAPCAS | cas.myadoptionportal.com | M | CAS | taskfreakCAS | quickbook_apiCAS | mapmachformCAS
14 | Cradle | MAPCRADLE | cradle.myadoptionportal.com | M | Cradle | taskfreakCRADLE | quickbook_apiCRADLE | mapmachformCRADLE
114 | Cradle old | MAPCRADLE1 | cradle1.myadoptionportal.com | M | cradledemo | taskfreakCRADLE1 | quickbook_apiCRADLE1 | mapmachformCRADLE1
104 | Deaconess Pregnancy and Adoption Services | MAPDPAS | dpas.myadoptionportal.com | M | DPAS | taskfreakDPAS | quickbook_apiDPAS | mapmachformDPAS
157 | dev.myadoptionportal.com | MyAdoptionPortalDev | dev.myadoptionportal.com | M | Demo | taskfreakDEV | quickbook_apiDEV | mapmachformDEV
151 | devroles.myadoptionportal.com | MyAdoptionPortalRoleDev | devroles.myadoptionportal.com | R | MapRole | taskfreakDEVROLES | quickbook_apiDEVROLES | mapmachformDEVROLES
133 | Eckerd Community Alternatives | MAPECKERD | eckerd.myadoptionportal.com | M | ECA | taskfreakECKERD | quickbook_apiECKERD | mapmachformECKERD
140 | Embraced by Grace | MAPebg | ebg.myadoptionportal.com | M | EBC | taskfreakEBG | quickbook_apiEBG | mapmachformEBG
67 | European Children Adoption Services | MAPECAS | ecas.myadoptionportal.com | M | ECAS | taskfreakECAS | quickbook_apiECAS | mapmachformECAS
17 | Family Adoption Consultants | MAPFAC | fac.myadoptionportal.com | M | fac | taskfreakFAC | quickbook_apiFAC | mapmachformFAC
52 | Hawaii International Child | MAPHIC | hic.myadoptionportal.com | M | hicold | taskfreakHIC | quickbook_apiHIC | mapmachformHIC
95 | Heart of Adoptions, Inc. | MAPHOA | hoa.myadoptionportal.com | M | HOA | taskfreakHOA | quickbook_apiHOA | mapmachformHOA
88 | International Families, Inc. | MAPIFI | ifi.myadoptionportal.com | M | IFI | taskfreakIFI | quickbook_apiIFI | mapmachformIFI
51 | Little Miracles International Inc. | MAPLMI | lmi.myadoptionportal.com | M | lm | taskfreakLMI | quickbook_apiLMI | mapmachformLMI
45 | Living Hope Adoption Agency | MAPLH | lh.myadoptionportal.com | M | lh | taskfreakLH | quickbook_apiLH | mapmachformLH
131 | Lutheran Social Services Of Montana | MAPLSSMT | lssmt.myadoptionportal.com | M | LSM | taskfreakLSSMT | quickbook_apiLSSMT | mapmachformLSSMT
79 | Media Systems | MAPDEMO | demo.myadoptionportal.com | M | Demo | taskfreakDEMO | quickbook_apiDEMO | mapmachformDEMO
113 | MTA2 | MAPMTA2 | mta2.myadoptionportal.com | M | MTA2 | taskfreakMTA2 | quickbook_apiMTA2 | mapmachformMTA2
124 | One World Adoption Services | MAPOWAS | owas.myadoptionportal.com | M | ona | taskfreakOWAS | quickbook_apiOWAS | mapmachformOWAS
28 | Premier Adoptions | MAPPAA | paa.myadoptionportal.com | M | paa | taskfreakPAA | quickbook_apiPAA | mapmachformPAA
117 | St. Mary's Services | MAPSMS | sms.myadoptionportal.com | M | sms | taskfreakSMS | quickbook_apiSMS | mapmachformSMS
33 | Sunny Ridge Family Center | MAPSR | sr.myadoptionportal.com | M | sr | taskfreakSR | quickbook_apiSR | mapmachformSR
125 | Surratt Law LLC | MAPSCL | scl.myadoptionportal.com | M | SL | taskfreakSCL | quickbook_apiSCL | mapmachformSCL
34 | TDH | MAPTDH | tdh.myadoptionportal.com | M | TDH | taskfreakTDH | quickbook_apiTDH | mapmachformTDH
164 | test.myadoptionportal.com | MyAdoptionPortalTest | test.myadoptionportal.com | M | Demo | taskfreakTEST | quickbook_apiTEST | mapmachformTEST
119 | Zdoptions | MAPZDOPT | zdopt.myadoptionportal.com | M | Zdopt | taskfreakZDOPT | quickbook_apiZDOPT | mapmachformZDOPT

## Agency Password
agency_id | user_id | agency_name | c_account_key | Sub Domain Name | Status | Role | User Credentials
18 | 166 | A Chosen Child Inc. | 118 | acc.myadoptionportal.com |  | AA | linda@strowbridge.com/welcome1
|  |  |  | CW | clara@achosenchild.org | CW | clara@achosenchild.org/acc1599
|  |  |  | Agency | linda@strowbridge.com | AP | csmith5436@bellsouth.net/91906987
|  |  |  | a. Sign-up | Domain was showing up
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
34 | 366 | A Gift of Life | 122 | gol.myadoptionportal.com |  | AA | cstill@giftoflifeadoptions.com/abc123
|  |  |  | user does not exists | info@giftoflifeadoptions.com | CW | atomljanovich@giftoflifeadoptions.com/abc123
|  |  |  | Agency | cstill@giftoflifeadoptions.com | AP | ajortmann@gmail.com/panther
|  |  |  | a. Sign-up | Domain was showing up
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
37 | 384 | Adams Agency | 121 | adam.myadoptionportal.com
|  |  |  | Was not able to figure out Agency password | Adam@adoptsoft.com
38 | 437 | Adoption Alliance - Colorado | 15 | aa.myadoptionportal.com |  | AA | Kristeng@adoptall.org
|  |  |  | the user does not exists | info@adoptall.org | CW | Officemgr@adoptall.org/welcome1
|  |  |  | Was not able to figure ut Agency password | Kristeng@adoptall.org | AA | Kristeng@adoptall.org
59 | 1554 | Adoption Alliance - Texas | 108 | aat.myadoptionportal.com |  | AA | justin@adoptionalliance.com/welcome1
|  |  |  | Agency | justin@adoptionalliance.com | CW | Officemgr@adoptall.org/welcome1
|  |  |  | a. Sign-up | Domain was showing up | AP | AlanNicole@aa.com/4321
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
22 | 214 | Adoption and Family Support Center | 120 | afsc.myadoptionportal.com |  | AA | angelaquick@hotmail.com/manifest2011!
|  |  |  | CW | elisa568@yahoo.com | CW | elisa568@yahoo.com /welcome1
|  |  |  | Agency |  | AP | abby.gift@yahoo.com/abby.gift@yahoo.com
|  |  |  | a. Sign-up | Domain was showing up
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
28 | 324 | Adoption Associates Inc. | 109 | aai.myadoptionportal.com |  | AA | mleahy@adoptionassociates.net/Str82The.
|  |  |  | Agency | adopt@adoptionassociates.net | CW | adickson@adoptionassociates.net/welcome1
|  |  |  | a. Sign-up | Domain was showing up | AP | aaquila.buffshep@gmail.com/aaquila.buffshep@gmail.com
|  |  |  | b. Sign-in | Domain was showing up |  | mleahy@adoptionassociates.net/Str82The.
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
27 | 304 | Adoption Dreams Come True | 101 | adct.myadoptionportal.com |  | AA | adoptdreams@yahoo.com/dreams0613
|  |  |  | Agency | adoptdreams@yahoo.com | CW | cindalopez@gmail.com/dreams0613
|  |  |  | a. Sign-up | Domain was showing up | AP | amyritt@aol.com/welcome1
|  |  |  | b. Sign-in | Domain was showing up |  | adoptdreams@yahoo.com / adopt1
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
35 | 380 | Adoption Related Services, Inc. | 123 | ars.myadoptionportal.com |  | AA | barblorenzo@comcast.net/welcome1
|  |  |  | the user does not exists | info@adoption-related-services.org | CW | estump@ars.com/welcome1
|  |  |  | Agency | barblorenzo@comcast.net | AP | adam@mediaus.com/adam123
|  |  |  | a. Sign-up | Domain was showing up
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
25 | 257 | Adoptions Together | 6 | at.myadoptionportal.com |  |  | mapadmin@adoptionstogether.org /ATmap@dm1n
|  |  |  | CW(Was not able to login as CW) | abache@adoptionstogether.org | AA | info@ad-in.org/abc123
|  |  |  | Agency | mapadmin@adoptionstogether.org | CW | allie@beaconhouseadoption.com/welcome1
|  |  |  | a. Sign-up | Domain was showing up | AP | amcclung@richmond.edu/8896amcclung@richmond.edu
|  |  |  | b. Sign-in | Domain was showing up |  | abache@adoptionstogether.org / Silly924
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
39 | 457 | All Blessings International | 66 | abi.myadoptionportal.com |  | AA | adopt@allblessings.org/welcome1
|  |  |  | Agency | adopt@allblessings.org | CW | diana@allblessings.org/welcome1
|  |  |  | a. Sign-up | Domain was showing up | AP | daisy@map.com/welcome1
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
61 | 1876 | ALPTEST | 127 | alptest.myadoptionportal.com |  | AA
|  |  |  | Agency | info@AdoptionLearningPartners.org | CW | Not able t ofind password
|  |  |  | a. Sign-up | Domain was showing up | AP
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
26 | 266 | CAIRS Solutions | 132 | cairs.myadoptionportal.com |  | AA | Mark@adoptsoft.com/abc123
|  |  |  | Agency | mark.livings@cairsolutions.com | CW | betty@gmail.com/abc123
|  |  |  | a. Sign-up | Domain was showing up | AP | bidisha.ghosh@cairsolutions.com/abc123
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
81 | 6591 | Catholic Charities of Dallas | 139 | ccd.myadoptionportal.com |  | AA | admin@catholiccharitiesdallas.org/welcome1
|  |  |  | Agency | admin@catholiccharitiesdallas.org | CW | btentroek@central.catholiccharitiesdallas.org/welocme1
|  |  |  | a. Sign-up | Domain was showing up | AP | dsnapp@dcdiocese.org/ds9035
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
74 | 6148 | Catholic Charities of Northern Kansas | 138 | cck.myadoptionportal.com |  | AA | khauser@catholiccharitiessalina.org/adoptionsalina
|  |  |  | Agency | khauser@catholiccharitiessalina.org | CW | ghodges@ccnks.org/hayskansas
|  |  |  | a. Sign-up | Domain was showing up | AP | daveh83@aol.com/dlhmat
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
58 | 1423 | Catholic Charities of Southern Nevada | 126 | ccn.myadoptionportal.com |  | AA | admin@catholiccharities.com/welcome1
|  |  |  | AP | adoptionservices@catholiccharities.com | CW | bsingletary@catholiccharities.com/adoption
|  |  |  | Agency | admin@catholiccharities.com | AP | ukcrouch1@yahoo.com/tangerine
|  |  |  | a. Sign-up | Domain was showing up
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
10 | 98 | Catholic Social Service, Dodge city | 1 | css.myadoptionportal.com
|  |  |  | Agency | adopt@catholicsocialservice.org | AA | adopt@catholicsocialservice.org/kcroyals85!
|  |  |  | a. Sign-up | Domain was showing up | CW | afalcon@catholicsocialservice.org/10AFswcss
|  |  |  | b. Sign-in | Domain was showing up | AP | abby5179@hotmail.com/colo2008
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
68 | 2844 | Catholic Social Services of Montana | 99 | cssmt.myadoptionportal.com |  | AA | admin@cssmt.org/Bidisha
|  |  |  | User does not exists | helena@cssmt.org | CW | becky@cssmt.org/adoption
[6 empty] | AP | jwhitlock@mt.gov/treyreid16
|  |  |  | a. Sign-up | Domain was showing up |  | admin@cssmt.org/ServantLeader
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
72 | 4018 | Catholic Social Services, Alaska | 91 | cssa.myadoptionportal.com |  | AA | admin@cssalaska.org/welcome1
|  |  |  | User does not exists | sbomalaski@cssalaska.org | CW | neematest@gmail.com/neematest
|  |  |  | Agency | admin@cssalaska.org | AP | No AP
|  |  |  | a. Sign-up | Domain was showing up
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
17 | 190 | Christian Family Services | 105 | cfs.myadoptionportal.com |  | AA | moniquel@cfsfl.org/welcome1
|  |  |  | CW -Was not able to figure out password | info@cfsfl.org | CW | debbiec@cfsfl.org/cfs1978
|  |  |  | AA -Was not able to figure out password | moniquel@cfsfl.org | AP | akeelin@bellsouth.net/adoption
79 | 5894 | Connections Adoption Services, Inc. | 87 | cas.myadoptionportal.com |  | AA | admin@connectionsinfo.com/welcome1
|  |  |  | User does not exists | mary@connectionsinfo.com | CW | No
|  |  |  | Agency | admin@connectionsinfo.com | AP | No
|  |  |  | a. Sign-up | Domain was showing up
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
54 | 868 | Cradle | 14 | cradle.myadoptionportal.com |  | AA | CAIRSadmin@cradle.org/60201adopt
|  |  |  | Agency | CAIRSadmin@cradle.org | CW | bhann@cradle.org/60201adopt
|  |  |  | a. Sign-up | Domain was showing up | AP | at142@yahoo.com/123456
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
1 | 11 | Cradle old | 114 | cradle1.myadoptionportal.com |  | AA | CAIRSadmin@cradle.org/60201adopt
|  |  |  | User does not exists | support@cradle.org | CW
43 | 600 | Cradleold2 | 114 | cradle2.myadoptionportal.com |  | AP | krw17princess@aim.com/dantre123
|  |  |  | User does not exists | support@cradle.org
82 | 6753 | Embraced by Grace | 104 | ebg.myadoptionportal.com |  | AA | adoption@embracedbygrace.org/abc123
|  |  |  | Agency | adoption@embracedbygrace.org | CW | NO
|  |  |  | a. Sign-up | Domain was showing up | AP | jayan@jayan.com/jayan@jayan.com
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
77 | 5017 | Family Adoption Consultants | 17 | fac.myadoptionportal.com |  | AA | adoption@fcsohio.org/abc123
|  |  |  | The user does not exists | kathyluz@facadopt.org | CW | azfac96@yahoo.com/abc123
|  |  |  | Agency | admin@facadopt.org | AP | colemarye@hotmail.com/Anniemutt01
|  |  |  | a. Sign-up | Domain was showing up
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
42 | 597 | Hawaii International Child | 52 | hic.myadoptionportal.com |  | AA | lockout@gmail.com/My$0.02
|  |  |  | CW | KCastagnaro@h-i-c.org | CW | cindy@h-i-c.org/welcome1
|  |  |  | Agency | lockout@gmail.com | AP | setsuri2003@yahoo.com/adoptionroad
|  |  |  | a. Sign-up | Domain was showing up
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
21 | 194 | Heart of Adoptions, Inc. | 95 | hoa.myadoptionportal.com |  | AA | tammi@heartofadoptions.com/coco2010
|  |  |  | CW | jessica@heartofadoptions.com | CW | annsley@heartofadoptions.com/hokies
|  |  |  | Agency | tammi@heartofadoptions.com | AP | hollymm@msn.com/ap8Iyixw
|  |  |  | a. Sign-up | Domain was showing up |  | admin@heartofadoptions.com/hoa123
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
78 | 5624 | Media Systems | 79 | demo.myadoptionportal.com |  | AA | hradmin@admin.com / hradmin@admin.com
|  |  |  | Agency | hradmin@admin.com | CW | cw@upload.com / cw@upload.com
|  |  |  | a. Sign-up | Domain was showing up | AP | aleena@payment.com /aleena@payemnt.com
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
24 | 613 | One World Adoption Services | 124 | owas.myadoptionportal.com |  | AA | sysadmin@oneworldadoptions.org /owas2013
|  |  |  | Agency | main@oneworldadoptions.org | CW | alex@oneworldadoptions.org /married09
|  |  |  | a. Sign-up | Domain was showing up | AP | andreawise@gmail.com /adoption
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
69 | 2864 | Premier Adoption | 28 | paa.myadoptionportal.com |  | AA | admin@premieradoption.org /welcome1
|  |  |  | User does not exists | isa@premieradoption.org | CW | tomas@premieradoption.org /welcome1
|  |  |  | Agency | admin@premieradoption.org | AP | truj2@live.com /welcome1
|  |  |  | a. Sign-up | Domain was showing up
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
16 | 185 | St. Mary's Services | 117 | sms.myadoptionportal.com |  | AA | hfitzpatrick@stmaryservices.com /welcome1
|  |  |  | The user does not exists | information@stmaryservices.com | CW | cbuck@stmaryservices.com /welcome1
|  |  |  | AA -Was not able to figure out password | hfitzpatrick@stmaryservices.com | AP | cindyd333@hotmail.com
32 | 347 | Sunny Ridge Family Center | 33 | sr.myadoptionportal.com
|  |  |  | Agency | kgraham@sunnyridge.org
|  |  |  | a. Sign-up | Domain was showing up | AA | kgraham@sunnyridge.org /welcome1
|  |  |  | b. Sign-in | Domain was showing up | CW | NO
|  |  |  | c. Machform badge | Domain was showing up | AP | NO
|  |  |  | d. Event badge | Domain was showing up
57 | 1419 | Surrogacy Choices LLC | 125 | scl.myadoptionportal.com |  | AA | surrattlaw@gmail.com /welcome1
|  |  |  | Agency | kgraham@sunnyridge.org | CW | sccw@gmail.com/ abc123
|  |  |  | a. Sign-up | Domain was showing up | AP | slip1@gmail.com /welcome1
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
19 | 174 | TDH | 34 | tdh.myadoptionportal.com |  | AA | dorinda@tdh.ca/robin1
|  |  |  | Agency | dorinda@tdh.ca | CW | emi@tdh.ca/welcome1
|  |  |  | a. Sign-up | Domain was showing up | AP | anhhuyen@live.ca/uliv1s
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
20 | 355 | Zdoptions | 119 | zdopt.myadoptionportal.com |  | AA | info@zdoptions.com/Adoption1
|  |  |  | Agency | info@zdoptions.com | CW | NO
|  |  |  | a. Sign-up | Domain was showing up | AP | bbstest@map.com/pepper
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
44 | 695 | Living Hope Adoption Agency | 45 | lh.myadoptionportal.com
|  |  |  | Agency | info@livinghopeadoption.org | AA | info@livinghopeadoption.org/welcome1
|  |  |  | a. Sign-up | Domain was showing up | CW | esicilia@livinghopeadoption.org/welcome1
|  |  |  | b. Sign-in | Domain was showing up | AP | renee.wimbish@yahoo.com/pebbles
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
71 | 3035 | Eckerd Community Alternatives | 133 | eckerd.myadoptionportal.com |  |  | admin@eckerd.com/Sgraham123
|  |  |  | Agency | cgoing@eckerd-eca.org | AA | cgoing@eckerd-eca.org/welcome1
|  |  |  | a. Sign-up | Domain was showing up | CW | testcase@mediaus.com/nikhil
|  |  |  | b. Sign-in | Domain was showing up | AP | nikhiltest@gmail.com/nikhil
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
66 | 2559 | Lutheran Social Services Of Montana | 131 | lssmt.myadoptionportal.com |  | AA | lssmtadmin@lssmt.org/welcome1
|  |  |  | Agency | lssmtadmin@lssmt.org | CW | carries@lssmt.org/orphancare
|  |  |  | a. Sign-up | Domain was showing up | AP | arntzens@gmail.com/welcome1
|  |  |  | b. Sign-in | Domain was showing up
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
83 | 6774 | Adoptions of Indiana | 141 | aoi.myadoptionportal.com |  | AA | info@adoptionsofindiana.org/adopt12345
|  |  |  | a. Sign-up | Domain was showing up | CW | amontgomery@ad-in.org /welcome1
|  |  |  | b. Sign-in | Domain was showing up | AP | meg.sterchi131@gmail.com /abc123
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
|  | Beacon House adoptions |  | bh.myadoptionportal.com |  | AA | admin@beaconhouseadopt.com /welcome1
|  |  |  | a. Sign-up | Domain was showing up | CW | allie@beaconhouseadoption.com/welcome1
|  |  |  | b. Sign-in | Domain was showing up | AP | amcclung@richmond.edu/8896amcclung@richmond.edu
|  |  |  | c. Machform badge | Domain was showing up
|  |  |  | d. Event badge | Domain was showing up
30 | 338 | Little Miracales | 51 | lmi.myadoptionportal.com |  | AA | lmiadmin@littlemiracles.org/welcome1
76 | 4816 | International Families, Inc. | 88 | ifi.myadoptionportal.com |  | AA | info@ifiadopt.org/welcome1
|  | MAPS-Worldwide/Stepping Stones |  | mapsw.myadoptionportal.com |  | AA | admin@maps-worldwide.org / abc123
admin@maps-worldwide.org/heather
177 | 8125 | The R House Consultants | 117 | trh.myadoptionportal.com |  | AA | admin@therhouseadoptions.com / abc123
92 | 8125 | stageSDC (San Diego Council) | 186 | stagesdc.myadoptionportal.com |  | AA | stagesdc@myadoptionportal.com/stagesdc@myadoptionportal.com
69 | 2864 | stagepa (Premier Adoptions) | 187 | stagepa.myadoptionportal.com |  | AA | stagepa@myadoptionportal.com/stagepa@myadoptionportal.com
190 | 8125 | Adoption Advocate | 190 | aadv.myadoptionportal.com |  | AA | admin@adoptionadvocates.org / abc123
191 | 8125 | DRC | 191 | drc.myadoptionportal.com |  | AA | admin@drcadoptionservices.com / abc123
192 | 8125 | AGAPE | 192 | agape.myadoptionportal.com |  | AA | admin@agapeforchildren.com/abc123
|  | chrysalishouse |  |  |  |  | admin@chrysalishouse.com / abc123
194 | 8125 | [5 empty] | admin@childrenoftheworld.com/abc123
CWmedia2301@gmail.com
|  | Demo |  | www.myadoptionportal.com |  |  | rolesmedia@mediaus.com/rolesmedia@mediaus.com
|  | Test/Mapdev |  | test.myadoptionportal.com |  |  | hradmin@admin.com/hradmin@admin.com
|  | Rolesdev |  |  |  |  | devroles@myadoptionportal.com/devroles@myadoptionportal.com
|  | Portal Admin |  | www.myadoptionportal.com |  |  | admin/myadoptionportal
|  | SDC |  | sdc.myadoptionportal.com |  |  | admin@sdc.com / Adoption456
|  | Full Circle Adoption |  | fullcircleadoptions.myadoptionportal.com |  |  | admin@fullcircleadoptions.com / 123456
|  | Buckner |  | buckner.myadoptionportal.com |  |  | info@buckner.org / buckner123
|  | Dillonadopt |  | https://dillonadopt.myadoptionportal.com |  |  | admin@dillonadopt.com/dillonmaps
|  | Forever Bound Adoption |  | MAPFBA |  |  | admin@foreverboundadoption.org/123456
|  | qaroles |  |  |  |  | qaroles@myadoptionportal.com/qaroles@myadoptionportal.com
|  | Heart of adoption alliance | HOAA |  |  |  | admin@heartofadoptionsalliance.com/hoa2012
|  | Childrenoftheworld | cotw |  |  |  | admin@childrenoftheworld.com/abc123
|  |  | CCDIOBR |  |  |  | admin@ccdiobr.org/adopt1964
|  | RolesStage |  |  |  |  | stageroles@myadoptionportal.com / stageroles@myadoptionportal.com
|  | php myadmin pf server |  | http://192.168.1.50/ |  |  | root/I4GotIt
|  | 192.168.50.10 |  |  |  |  | map/Passw0rd
|  | 192.168.1.19 |  |  |  |  | sa/I4GotIt
|  | cairs staff login |  |  |  |  | map/abc123
|  | ctpf01-myadmin.parentfinder.com |  | ctpf01-myadmin.parentfinder.com |  |  | root/ I4GotIt
|  | Production server |  | 207.238.121.208/192.168.1.19 |  |  | Username:sql001\administrator
Password:G0#Sand

## Sheet3
SL. No. | Area | Agency | Description
1 | Post placement country wise dates fulfillment tracking and alerts and report | Dillon | Multiple Post placement dates viewable country wise per client and setting alerts for staff and reporting on a monthly basis on the dates that are due and that are completed
2 | Report | SDC/LSSMN/Dillon/AT/GOL/Haven Adoptions | Fast fact dates reporting. This is required for Background clearance, Post placement schedules and other dates which requires renewal

## Sheet2
-325 | USCIS adoptee approval | Insert into table (a,b) select -325,'USCIS adoptee approval'
-324 | USCIS fingerprints | Insert into table (a,b) select -324,'USCIS fingerprints'
-323 | USCIS application | Insert into table (a,b) select -323,'USCIS application'
-322 | Travel-second trip | Insert into table (a,b) select -322,'Travel-second trip'
-321 | Travel-first trip | Insert into table (a,b) select -321,'Travel-first trip'
-320 | Refundable deposit | Insert into table (a,b) select -320,'Refundable deposit'
-319 | Publicity Consent | Insert into table (a,b) select -319,'Publicity Consent'
-318 | Psychological evaluation | Insert into table (a,b) select -318,'Psychological evaluation'
-317 | Post placement reports | Insert into table (a,b) select -317,'Post placement reports'
-316 | Post placement documents | Insert into table (a,b) select -316,'Post placement documents'
-315 | Placement | Insert into table (a,b) select -315,'Placement'
-314 | On hold | Insert into table (a,b) select -314,'On hold'
-313 | Medical clearance | Insert into table (a,b) select -313,'Medical clearance'
-312 | Interagency agreement | Insert into table (a,b) select -312,'Interagency agreement'
-311 | ICPC | Insert into table (a,b) select -311,'ICPC'
-310 | Home study | Insert into table (a,b) select -310,'Home study'
-309 | Family reports | Insert into table (a,b) select -309,'Family reports'
-308 | Embassy/Consulate | Insert into table (a,b) select -308,'Embassy/Consulate'
-307 | Dossier | Insert into table (a,b) select -307,'Dossier'
-306 | DNA | Insert into table (a,b) select -306,'DNA'
-305 | Court | Insert into table (a,b) select -305,'Court'
-304 | Citizenship | Insert into table (a,b) select -304,'Citizenship'
-303 | Background clearances | Insert into table (a,b) select -303,'Background clearances'
-302 | Assignment | Insert into table (a,b) select -302,'Assignment'
-301 | Arrival | Insert into table (a,b) select -301,'Arrival'
-300 | Adoption finalization | Insert into table (a,b) select -300,'Adoption finalization'

## Sheet4
-400 | -300 | Finalized in country | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -400,-300,'Finalized in country',5
-401 | -300 | Country decree received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -401,-300,'Country decree received',5
-402 | -300 | Finalized in U.S. | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -402,-300,'Finalized in U.S.',5
-403 | -300 | U.S. decree received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -403,-300,'U.S. decree received',5
-404 | -300 | U.S. decree sent to country | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -404,-300,'U.S. decree sent to country',5
-405 | -301 | Arrival date | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -405,-301,'Arrival date',5
-406 | -301 | Visa type | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -406,-301,'Visa type',5
-407 | -301 | Port of entry | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -407,-301,'Port of entry',5
-408 | -301 | Home airport | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -408,-301,'Home airport',5
-409 | -302 | Assignment accepted | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -409,-302,'Assignment accepted',5
-410 | -302 | Country case number | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -410,-302,'Country case number',5
-411 | -302 | Sent to country | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -411,-302,'Sent to country',5
-412 | -302 | Guardianship transferred | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -412,-302,'Guardianship transferred',5
-413 | -302 | Consent to adopt sent to family | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -413,-302,'Consent to adopt sent to family',5
-414 | -303 | Applicant/Resident | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -414,-303,'Applicant/Resident',5
-415 | -303 | Type | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -415,-303,'Type',5
-416 | -303 | Clearance Date | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -416,-303,'Clearance Date',5
-417 | -303 | Expiration Date | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -417,-303,'Expiration Date',5
-418 | -303 | Cleared | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -418,-303,'Cleared',5
-419 | -303 | USA State | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -419,-303,'USA State',5
-420 | -303 | Country | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -420,-303,'Country',5
-421 | -304 | Citizenship issued | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -421,-304,'Citizenship issued',5
-422 | -304 | Received from family | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -422,-304,'Received from family',5
-423 | -304 | Sent to country | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -423,-304,'Sent to country',5
-424 | -305 | POA signed | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -424,-305,'POA signed',5
-425 | -305 | Appointment date | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -425,-305,'Appointment date',5
-426 | -305 | Appointment time | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -426,-305,'Appointment time',5
-427 | -305 | Preliminary approval | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -427,-305,'Preliminary approval',5
-428 | -306 | Requested | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -428,-306,'Requested',5
-429 | -306 | Approved | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -429,-306,'Approved',5
-430 | -307 | Instructions sent | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -430,-307,'Instructions sent',5
-431 | -307 | Received from family | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -431,-307,'Received from family',5
-432 | -307 | Completed | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -432,-307,'Completed',5
-433 | -307 | Sent to country | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -433,-307,'Sent to country',5
-434 | -307 | Registered | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -434,-307,'Registered ',5
-435 | -307 | Approved | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -435,-307,'Approved',5
-436 | -307 | Dossier number | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -436,-307,'Dossier number',5
-437 | -308 | Case number | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -437,-308,'Case number',5
-438 | -308 | Birth parent interview | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -438,-308,'Birth parent interview',5
-439 | -308 | Visa appointment requested | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -439,-308,'Visa appointment requested',5
-440 | -308 | Visa appointment | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -440,-308,'Visa appointment',5
-441 | -309 | Required | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -441,-309,'Required',5
-442 | -309 | Complete by | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -442,-309,'Complete by',5
-443 | -309 | Received from family | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -443,-309,'Received from family',5
-444 | -309 | Sent to country | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -444,-309,'Sent to country',5
-445 | -310 | Type | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -445,-310,'Type',5
-446 | -310 | Social worker | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -446,-310,'Social worker',5
-447 | -310 | HS agency | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -447,-310,'HS agency',5
-448 | -310 | Requested | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -448,-310,'Requested',5
-449 | -310 | Draft received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -449,-310,'Draft received',5
-450 | -310 | Reviewed/revisions sent | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -450,-310,'Reviewed/revisions sent',5
-451 | -310 | Reviewed by | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -451,-310,'Reviewed by',5
-452 | -310 | Approved | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -452,-310,'Approved',5
-453 | -310 | Final received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -453,-310,'Final received',5
-454 | -310 | Expires | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -454,-310,'Expires',5
-455 | -311 | Required | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -455,-311,'Required',5
-456 | -311 | 100A filed | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -456,-311,'100A filed',5
-457 | -311 | 100A approved | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -457,-311,'100A approved',5
-458 | -311 | 100A expires | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -458,-311,'100A expires',5
-459 | -311 | 100B filed | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -459,-311,'100B filed',5
-460 | -311 | ICPC terminated | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -460,-311,'ICPC terminated',5
-461 | -312 | Agreement received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -461,-312,'Agreement received',5
-462 | -312 | Liability insurance received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -462,-312,'Liability insurance received',5
-463 | -312 | Agency license received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -463,-312,'Agency license received',5
-464 | -312 | Agency license expires | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -464,-312,'Agency license expires',5
-465 | -312 | Hague/COA certificated received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -465,-312,'Hague/COA certificated received',5
-466 | -312 | Hague/COA accreditation expires | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -466,-312,'Hague/COA accreditation expires',5
-467 | -313 | Applicant/Resident | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -467,-313,'Applicant/Resident',5
-468 | -313 | Completed | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -468,-313,'Completed',5
-469 | -313 | Expires | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -469,-313,'Expires',5
-470 | -314 | Requested | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -470,-314,'Requested',5
-471 | -314 | Expires | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -471,-314,'Expires',5
-472 | -315 | Placement | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -472,-315,'Placement',5
-473 | -316 | Arrival packet sent | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -473,-316,'Arrival packet sent',5
-474 | -316 | Country adoption/guardianship documents received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -474,-316,'Country adoption/guardianship documents received',5
-475 | -316 | Health exam form received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -475,-316,'Health exam form received',5
-476 | -316 | Lab test form received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -476,-316,'Lab test form received',5
-477 | -316 | Finalization packet sent | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -477,-316,'Finalization packet sent',5
-478 | -316 | Social Security number received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -478,-316,'Social Security number received',5
-479 | -316 | Will received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -479,-316,'Will received',5
-480 | -317 | Report number | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -480,-317,'Report number',5
-481 | -317 | Social worker | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -481,-317,'Social worker',5
-482 | -317 | PP agency | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -482,-317,'PP agency',5
-483 | -317 | Complete by | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -483,-317,'Complete by',5
-484 | -317 | Draft received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -484,-317,'Draft received',5
-485 | -317 | Reviewed/revisions sent | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -485,-317,'Reviewed/revisions sent',5
-486 | -317 | Reviewed by | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -486,-317,'Reviewed by',5
-487 | -317 | Approved | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -487,-317,'Approved',5
-488 | -317 | Final received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -488,-317,'Final received',5
-489 | -317 | Sent to country | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -489,-317,'Sent to country',5
-490 | -318 | Completed | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -490,-318,'Completed',5
-491 | -318 | Expires | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -491,-318,'Expires',5
-492 | -319 | Completed | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -492,-319,'Completed',5
-493 | -319 | Photo release for agency | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -493,-319,'Photo release for agency',5
-494 | -319 | Photo release for country | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -494,-319,'Photo release for country',5
-495 | -319 | Media coverage at arrival | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -495,-319,'Media coverage at arrival',5
-496 | -319 | Media coverage after arrival | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -496,-319,'Media coverage after arrival',5
-497 | -320 | Requested | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -497,-320,'Requested',5
-498 | -320 | Sent to family | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -498,-320,'Sent to family',5
-499 | -321 | Travel packet sent | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -499,-321,'Travel packet sent',5
-500 | -321 | Travel clearance number | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -500,-321,'Travel clearance number',5
-501 | -321 | Received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -501,-321,'Received',5
-502 | -321 | Departure | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -502,-321,'Departure',5
-503 | -321 | Arrival | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -503,-321,'Arrival',5
-504 | -322 | Travel packet sent | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -504,-322,'Travel packet sent',5
-505 | -322 | Travel clearance number | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -505,-322,'Travel clearance number',5
-506 | -322 | Received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -506,-322,'Received',5
-507 | -322 | Departure | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -507,-322,'Departure',5
-508 | -322 | Arrival | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -508,-322,'Arrival',5
-509 | -323 | Type | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -509,-323,'Type',5
-510 | -323 | Received by USCIS | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -510,-323,'Received by USCIS',5
-511 | -323 | Approved | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -511,-323,'Approved',5
-512 | -323 | Expires | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -512,-323,'Expires',5
-513 | -323 | RFE received | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -513,-323,'RFE received',5
-514 | -323 | RFE response submitted | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -514,-323,'RFE response submitted',5
-515 | -324 | Applicant/Resident | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -515,-324,'Applicant/Resident',5
-516 | -324 | Fingerprint Expires | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -516,-324,'Fingerprint Expires',5
-517 | -324 | Arrest history | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -517,-324,'Arrest history',5
-518 | -325 | Number of children | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -518,-325,'Number of children',5
-519 | -325 | Gender | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -519,-325,'Gender',5
-520 | -325 | Age range | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -520,-325,'Age range',5
-521 | -325 | Health status | Insert into CIListTemplateItem (CIListTemplateItemId,CIListTemplateId,CIListTemplateItemName,CIListItemTypeId) select -521,-325,'Health status',5

## Other Password
http://www.setasign.de | mark.livings@cairsolutions.com | adoption1
https://mailgun.com | mark.livings@cairsolutions.com | Str82The.
https://cpvpn01.cairsolutions.com/
CAIRS Solutions (to Me - Private):
username: mlivings
CAIRS Solutions (to Me - Private):
Password: Adoption1